## Bid
ArcheryNZ Premier Events |  |  | Updated: | 2020-09-10
Bid Checklist
Event:
LOC:
Item | Owner | Suggested Timeline | Status | Notes
Confirm support of club or district organisation (or other)
Prepare LOC structure, and recruit team members
Agree LOC objectives for running event
Develop Event Programme, check no clash with other major events (NZFAA, WA, other major sporting event in city)
Review suitable venues and confirm availability/cost
Seek budget quotations for major procurement items
Draft sponsorship and grants plan, have preliminary discussions with key funding sources if necessary
Develop event budget
Seek provisional reservation for venue(s)
Submit Bid to Archery NZ Premier Event Manager

## Planning
ArcheryNZ Premier Events |  |  | Updated: | 2020-09-10
Planning Checklist
Event:
LOC:
Item | Owner | Due Date | Status | Notes
GENERAL ADMINISTRATION
Determine a schedule for LOC meetings
Agree LOC Roles & Responsibilities
Confirm which documents need sponsor/event logos on them
Confirm pricing plan for event
Prepare Entry Form, invitation and outline programme for review by Administration Manager, TV Producer, Chief Judge (or Technical Delegate) and Archery NZ Premier Events Manager
Issue Entry Form, invitation and outline programme following feedback (include version date)
Prepare detailed programme for review by Administration Manager, TV Producer, Chief Judge (or Technical Delegate) and Archery NZ Premier Events Manager
Issue Detailed Programme following feedback (include version date)
Receive Entries and generate work in progress entries list
Confirm internet connectivity requirements for venue
Set up IANSEO for event
Prepare target draw
Prepare scoresheets
Prepare back numbers
VOLUNTEERS
Recruit Ground Crew for event operations (including manager for larger events)
Recruit volunteers for set up and pack down
Confirm Judges' Availability (via Technical Support Manager)
Recruit Runners for finals day
Recruit Announcer for finals day
Recruit Athlete Marshal for finals day
Recruit Admin Team Support (coordinate requirements with Administration Manager)
Recruit First Aid Officer (if applicable)
Recruit an 'expert archer' commentator to support the TV-streaming (if applicable)
Recruit photographer (e.g. for opening ceremony, medal ceremony and trophy ceremony/banquet)
Brief volunteers on their roles and responsibilities
PROCUREMENT (for purchase, sponsorship, hire, or loan) - check availability of equipment in Archery NZ containers to keep costs down
Major procurement items
Venue
Container Transport
Line Marking
Score sheet paper (waterproof)
Target Faces, including spares for replacement/damage
PA system
Radios
Portaloos and hygiene facilities, including servicing (at least 1 disabled)
Gazebos/Marquees
Lighting, including extension cords and cabling (if indoor)
Merchandise (if applicable)
TV streaming production (if applicable)
Spectator Stands (if applicable)
Banquet Venue and Catering (if applicable)
Medals
Accommodation for core admin team (3 people unless local) and judges from out-of-town
Other items
Meeting Room hire (if applicable)
Target Butts
Target Butt Backstops
Target Numbers
Target Flags
Score cards
Timing Lights and tripods
Match play score boards (for spectators)
Trailer Hire
Catering trucks
Meals and water for officials/Admin/crew
Water for competitors
Generator and spare diesel
Internet Access
Paper/printer/ink (admin team)
Laminating pouches (e.g. back numbers)
Cable ties for athlete numbers (admin team)
Stationary (admin team)
Music & Licensing
Security
Fencing
Riser for DOS if necessary
Uniforms for Crew (if applicable)
Event Logo design
Archer Registration Packs (incl. any give-aways)
Venue Dressing
Sunscreen
Signage
Advertising hoarding for behind presentations
Banquet Decoration (if applicable)
Banquet fees for VIPs (e.g. patron, sponsors)
Food/Drink for closing crew event
Thank you gifts for key officials/admin/crew
Flags
Flag Poles
Prize Money for match play (if applicable)
Opening/Closing Ceremony
Insurance (check with Archery NZ what is already covered)
Miscellaneous hardware
VENUE DESIGN
Confirm number of target butts required for qualification on field of play
Range should be directed as near to south as possible (preferably within 20 degrees) to avoid shooting into the sun
Confirm number of target butts required for match play on field of play, and at which ranges (coordinate with Administration Manager, as this has a strong impact on number of rounds required and length of day)
Confirm how many practice targets will be required at which distances during match play (e.g. for warm up for divisions who haven't had a practice at the start of the day) - coordinate with Administration Manager
Confirm number of spare target butts required for competition range
Confirm number of 5m blank butts required for warm-up (minimum of 5 blank butts for every 100 competitors)
Confirm target lane width
Determine any restraints for layout, e.g. rugby posts that cannot be removed, cricket pitches, underground drainage or sprinklers which may impact ability to hammer in pegs for butts/gazebos
Determine electricity requirements (DOS tent and Admin tent, catering trucks, PA system etc.), and locate generator if necessary. Consider risk of voltage drop from very long cords
Allow locations for timing lights
Allow locations for PA system and speakers
Include a location for catering trucks
Determine where the medal ceremony will be held, and any dressing requirements
Include fencing/barriers as necessary for safety
Confirm venue security requirements
Plan venue dressing to be used for 'look & feel'
Location for equipment inspection
Confirm where notice board/results will be posted at the grounds
Determine whether a 'Try Archery' activity can be set up, if the venue is likely to attract a large number of spectators
Confirm access requirements for venue (i.e. are gates open at a certain time, and will this suit operations?)
Confirm if limited vehicle access to the field of play is possible, as use of a car and trailer significantly speeds up work
Undertake risk assessment
Close out all items raised in risk assessment
Determine where blinds are required for finals, and what their construction will be
LOGISTICS
Confirm which containers are needed to be transported, where they will be transported from, and when they will need to be removed after the event
Book rooms for any meetings required e.g. officials, AGM
Book meeting room and dedicated toilet facility for anti-doping testing (confirm details with Archery NZ Anti-doping liaison)
Confirm who catering needs to be organised for (usually judges, admin team, crew, DOS for a simple lunch/water each day for the event)
Plan a thank-you event for volunteers following completion (e.g. a BBQ after pack-down)
Prepare a waste management plan (rubbish, recycling)
Liaise with Chief Judge regarding formation of a Jury of Appeal
COMMUNICATIONS
Develop Media plan for event
Prepare website and update regularly
Prepare social media accounts and update regularly
Arrange press release before the event
Arrange press releases during the event
Arrange press release at conclusion of the event
SPONSORSHIP
Develop a sponsorship plan, including levels of sponsorship, contribution requirements, and what can be provided for the sponsor
Approach and recruit sponsors
Identify sponsor logos for use, ensure they are used as agreed on documentation
Develop a sponsorship list/page for distribution, and inclusion in results booklet
GRANTS
Confirm which organisation is requesting grant funding - club or ANZ
Identify grants organisations to seek funding from, including local authorities, find out what their submission requirements are, and when their application dates are
Receive 3 comparable quotations for the major items where grant funding is sought - must be made out to the organisation seeking the grant funding (i.e. club or ANZ)
Submit funding applications in monthly tranches, and modify requests depending on which items are successful
Include grants providers on list of sponsors, and thank them for their contributions
Document and resolve grant requirements (i.e. keep receipts, take photographs of items in use, report as agreed)
OPENING CEREMONY
Determine style of event (e.g. demonstration, exhibition, opening arrow, or multiple items)
Confirm announcer/presenter
Confirm any VIPs to open event (e.g. Patron)
Prepare national anthem in a format that can be used for PA system
Ensure flags will be available for the grounds
Prepare ceremony script
MEDAL CEREMONIES
Order medals (check required numbers with Administration Manager) - include some spares which can be returned after the event for a minimal charge to replace centres
Determine if any special requirements for medal ceremonies (music, dressing, trays, marshals, podiums, flags)
Prepare ceremony script
Recruit Presenters
Confirm location of medal ceremonies
BANQUET AND AWARDS CEREMONY
Review venue options
Select venue
Select menu (ensure dietary requirements are communicated to the venue for individuals)
Determine if any decorations will be added to the venue
Prepare a script for the dinner and awards ceremony
Liaise with the Archery NZ to confirm which other awards may be awarded (e.g. team shields)
Liaise with the Trophy Steward for receipt of trophies, and prepare a table to receive/set out trophies
Confirm whether a liquor license is required for the event (no alcohol at youth-only events)
Determine whether a table(s) will be set aside for VIPs, e.g. Patron, sponsors, LOC etc.
Recruit MC
Recruit Presenters
TV STREAMING
Refer to supplier guidance on requirements
SOCIAL EVENTS
Develop a plan for any social events (e.g. welcome event, thank you BBQ for helpers)

## Operations
ArcheryNZ Premier Events |  |  | Updated: | 2020-09-10
Operations Checklist
Event:
LOC:
Item | Owner | Suggested Timeline | Status | Notes
VENUE SETUP (including finals venue)
Mow field (if necessary) and ensure field is not then mowed until after competition is completed
Set out and mark lines (strongly recommend being present if contractor is undertaking), including target lanes, target centres, athlete space on line. Do not start rest of build until the target and shooting lines are established
Install portaloos
Erect pterodactyls for moving target butts (or preferably use a trailer)
Rotate/replace centres of targets which are shot out
Move target butts to positions for official practice, including blank butt (keep same type of butts for same division if possible, some frames are different heights) - then erect, align so that centre of target face is above the line and secure targets (peg down outdoor, sandbag or screw indoor)
Attach back stops to targets most likely to need it (primarily compound, including juniors/masters)
Install distance markers at ends of each distance
Install target butt wind flags
Add about 14 target butt pins to the side of each target butt
Place target numbers at target (single-sided large numbers) and at 2m in front of shooting line (double-sided small numbers)
Install safety barriers
Place flag poles and raise flags and windsocks (flag poles can be duct-taped to two driven fence posts if needed)
Install and test PA system
Install and test lights & timing equipment
Install match play scoreboards (when needed)
Erect DOS tent
Erect Admin/Results tent
Erect tables and chairs for athletes (reserve some for equipment inspection, judges, DOS, admin)
Erect Gazebos/marquees
Install venue dressing - e.g. tear drop flags
Install wayfinding/signage
Install water station(s)
Put out rubbish/recycling bins
Cover exposed cables
Lay out new target faces flat so that they uncurl overnight - fold corners in line with judges' recommendations.
Undertake a site hazard assessment following set-up to identify any risk areas that need to be addressed
Tools needed on the day:
Metal Detectors
Hammers (in container)
Chisels (in container)
General tool box with miscellaneous items
Arrow pullers
Battery Drills (minimum 2x)
Duct Tape
Vehicle with trailer
Hi-vis vests or similar identifier for crew (some hi-vis in containers)
Gloves (some in container)
Spray paint
OFFICIAL PRACTICE
Check for any damage to equipment following setup
Place used target faces on butts (consider that each discipline distance shot needs to have the option to shoot on the right target at the right distance throughout the practice session) - target height gauges in container
Set out items which could not be left overnight (e.g. timing equipment on charge, PA system, tear drop flags, toblerones, etc.)
Test timing lights
Commence practice
OPENING CEREMONY
Follow LOC run sheet prepared for opening ceremony
If there is an opening arrow, bring a target forward in distance (if needed)
QUALIFICATION
Move target butts to correct locations for start of qualification, align and secure
Put up new target faces at correct heights
Send out score cards to each target
Scorecards to be brought back every 6 ends for results team to publish an update of score online (if not using electronic scoring)
Replace shot-out target faces and target butts as necessary
Support search for lost arrows with metal detectors - keep a list of description of any lost arrows, and expected lcoations, to support a continuation of the search later if they are not found
Support removal of arrows from target frames etc. with hammer, chisel, arrow pullers as needed
FINALS
as for "Venue Setup", plus:
Erect blinds
Erect spectator seating (if applicable), roping off areas in L or U shapes to allow spectators to get closer to the action
Erect tent for TV production
Brief TV camera operators and crew on safety
2x Arrow tubes for runners
Set up spotting scope(s) for announcer
MEDAL CEREMONY
Set up podiums
Set up dressing
Set up table(s) for medals and trays/awards
Brief presenter and support team on process
Receive a list of medal winners, in order of divisions awarded, and order of award (3rd, 2nd, 1st)
Set out medals on table by division for speed and clarity
After last award - consider a handing over of the WA flag to the LOC fo the next event, if it is known, or identify a better time to do this
BANQUET AND AWARDS CEREMONY
Decorate venue (if not already)
Reserve tables for VIPs (sponsors, patron, etc.)
Set up tables for trophies, awards and gifts
Enjoy the night, you deserve it!
PACK DOWN
Confirm with Archery NZ Premier Events Manager if any special requirements for packing containers for next event
Prepare container Inventory Lists to amend as they are packed
Retain sufficient used target faces to fully cover the practice day of the next event (with some spares), then the LOC may gift the remainder to the club or clubs who have been the major contributers to the event
Load containers securely for transport, and safely for unpacking at the next event - take photos on items as they are added so the next organiser can understand the general condition/volume of items
Celebrate and Relax!!!
Lessons Learned session
Submit final report |  | 1 month from end of event