## Sheet1
ArcheryNZ Premier Events - National Outdoor Champs |  |  |  | 2020-09-10
Roles & Responsibilities Matrix
X = Responsible
Item | Local Organising Committee (LOC) | ANZ Premier Events | ANZ Admin Team | ArcheryNZ Board
Event Initiation
Plan event requirements (e.g. rounds) |  | X
Advertise bid for event |  | X
Submit event bids, including budget and programme | X
Review event bids |  | X
Award event bids |  |  |  | X
Draft Memorandum of Understanding (MoU) |  | X
Sign MoU | X |  |  | X
Event Planning
Secure personnel for key organising committee roles | X
Secure personnel for administration team |  | X (Admin Team)
Hold meetings to plan event detail | X
Register event with ArcheryNZ and World Archery | X
Procurement of equipment | X
Arranging Delivery & Pickup of containers | X | consult
Develop event H&S Plan and hazard register | X | consult
Order medals | X
Seek returns, and award trophies (by Trophy Steward) |  | X (Trophy Steward)
Apply for grants | X
Advise of any existing ANZ sponsorship agreements, and sponsorship policy |  | X
Seek out sponsorship | X
Set entry fees | X
Set Programme | X
Select Venues for events, meetings & awards | X
Liaise with NZDFS for drug-testing requirements |  | X (via NZDFS liaison only)
Provide suitable facilities for drug-testing (if required) | X
Provide monthly reporting on event planning to Major Events team | X
Provide 3-monthly summary of programme of events status to Board |  | X
Appoint a Director of Shooting |  | X (Technical Support)
Appoint Judges |  | X (Technical Support)
Appoint an Appeals Committee | X
Plan social events (if required) | X
Set date for meetings (if required) | X (others) |  |  | X (AGM)
Venue layout, including line marking | X | consult | consult
Prepare radios (if necessary) and timing systems | X
PA system (if necessary) | X
Order Target Faces | X
Plan press releases for media | X
Transport and Accommodation for admin team (if not local) | X
Transport and Accommodation for judges (if not local) | X
IANSEO setup |  |  | X
Secure presenters for medal/trophy ceremonies | X
Entry Form
Prepare entry form | consult |  | X
Approve entry form |  | X
Issue and publicise entry form (on ANZ website for at least 24h before elsewhere) | X
Receive and track entries | consult |  | X
Venue Operations
Provide and coordinate volunteers, including ground crew, scoring helpers | X
Erect all equipment (e.g. target butts, DOS box, gazebos, flag poles, tables, chairs, safety barriers, etc.) and move as required | X
Provide lunches for officials, judges and crew on event days (and set-up/pack-down days if appropriate) | X
Portaloos (if required) | X
Archer Numbers (if required) |  |  | X
Registration Packs (if required) | X |  | consult
Target Draws (incl. matchplay) |  |  | X
Score Sheets |  |  | X
Undertake registration |  |  | X
Issue Media Passes |  |  | X
Results |  |  | X
Site security (if required) | X
Rubbish removal | X
Entertainment (if required), e.g. music | X
Coordinate Banquet, incl. presenters (if applicable) | X
Organise photographer (if applicable) | X
Necessary repairs to equipment (funded by ANZ with prior approval) | X
After Event
Document Container Inventory (consult Major Events regarding next events' container requirements) | X | consult
Present final detail of event finances and an event report, with lessons learned where applicable | X
Send Results to Ranking Administrator, Publicity Officer, others as required |  |  | X